## Sheet1
Date | Day | Task Title | Details | Remarks
2025-08-01 | Day 1 | 🔧 Project Setup | Initialize frontend (create-react-app / vite) Setup backend (express, mongoose, dotenv, cors) Connect frontend & backend Create folder structure
2025-08-02 | Day 2 | 👤 User Authentication (Backend) | Create User model Register & Login API Hash passwords with bcrypt Generate JWT tokens
2025-08-03 | Day 3 | 👤 User Auth (Frontend) | Register & Login UI using React Call backend APIs with Axios Store JWT token in localStorage Show login/register forms with validation
2025-08-04 | Day 4 | 🔐 Protected Routes & Role-Based Auth | Create PrivateRoute component Setup user role check (admin, user) Create Dashboard routes for both roles
2025-08-05 | Day 5 | 📦 Product Module (Backend) | Create Product model Add product APIs (CRUD) with validation Image upload (multer or cloudinary optional)
2025-08-06 | Day 6 | 📦 Product Module (Frontend - Admin) | Admin UI to Add/Edit/Delete products Product list table with actions
2025-08-07 | Day 7 | 🛒 Product Listing (User Side) | Product display page with cards Search, filter by category/price Product details view
2025-08-08 | Day 8 | 🛒 Cart Functionality | Add to cart button Local state/cart context or Redux Cart page: quantity + remove item
2025-08-09 | Day 9 | 📦 Order Module (Backend) | Order model (linked to user) Place order API (with total) Order status update API (for admin)
2025-08-10 | Day 10 | 📦 Order Module (Frontend) | Place order button on cart page “My Orders” page for users Order table for admin (update status)
2025-08-11 | Day 11 | 📊 Admin Dashboard | Show counts: users, orders, sales, products Charts using Chart.js or Recharts (optional)
2025-08-12 | Day 12 | ⚙️ Profile Management | User profile page (view/update) Admin: View/Edit/Delete users
2025-08-13 | Day 13 | 📁 Report Export + Email Setup | Export orders/sales data to CSV Send order confirmation via nodemailer
2025-08-14 | Day 14 | 🧪 Testing & Validation | Validate all forms and APIs Test protected routes Fix bugs and optimize code
2025-08-15 | Day 15 | 🚀 Deployment & Final Touches | Deploy backend (Render, Railway, etc.) Deploy frontend (Vercel/Netlify) Connect with MongoDB Atlas Final testing & README write-up